## Sheet1
Date | Estimate Duration Time | Start Time | End Time | Break Time | Duration Time | Error % | Adjusted estimate Duration Time | Description
2023-03-07 | 0.25 | 11:00 | 11:20 | 0 | 0.33 | 133 | 0.33 | I created a new Unity project and set up the scene with a floating platform, a plane and a simple character controller.
2023-03-07 | 0.5 | 11:20 | 12:10 | 10 | 0.66 | 132 | 0.66 | Created two scripts called "MovingPlatformController" and "WayPoints" that used "transform.rotation" and "Quarternion.Lerp" to rotate the platform.
2023-03-08 | 0.16 | 14:30 | 14:45 | 0 | 0.25 | 136.2637 | 0.21802 | Component was too small, therefore, wanted to create a respawn checkpoint system. I created a new Unity project and set up the scene with 2 empty game objects, a plane and a simple character controller.
2023-03-08 | 0.5 | 14:50 | 15:20 | 5 | 0.41 | 117.0213 | 0.58511 | found and followed a tutorial online that was based on a 2D game and was therefore using Vector2.
2023-03-08 | 0.5 | 15:20 | 15:40 | 0 | 0.33 | 103.6649 | 0.51832 | Created three scripts: "CheckpointController", "PlayerPos" and "RespawnCheckpoints".
| 0.75 |  |  |  | 0.99
| 0.91 |  |  |  | 1.24
| 1.41 |  |  |  | 1.65
| 1.91 |  |  |  | 1.98